## Bug Report Log
BANGBET KENYA — BUG REPORT LOG
Mobile QA — Android & iOS App Testing
Project: | BangBet Kenya App |  | Date Started:
Platform: | Android / iOS |  | Date Closed:
Tester Name: | Anthony Wambua |  | Environment: | Staging / Production
Test Cycle: | e.g. v3.2.1 Pre-Release |  | Build Version:
Bug ID | Date Reported | Reported By | Module / Feature | Bug Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Dev Notes / Fix
BG-001 | 28/05/2026 | Anthony Wambua | Login | App crashes on login with incorrect password (3rd attempt) | 1. Open app 2. Enter wrong password 3. Repeat 3 times | Error message shown: 'Incorrect password. Try again.' | App crashes and closes completely on 3rd failed attempt | Critical | P1 | Open
BG-002 | 28/05/2026 | Anthony Wambua | Deposit / M-Pesa | M-Pesa STK push not triggered on deposit screen | 1. Log in 2. Go to Deposit 3. Enter amount 4. Select M-Pesa 5. Tap Confirm | M-Pesa STK push prompt appears on user's phone within 10 seconds | No STK push received; deposit screen shows 'Processing' indefinitely | Critical | P1 | Open
BG-003 | 28/05/2026 | Anthony Wambua | Sports Betting | Odds not updating in real-time on live match screen | 1. Open a live football match 2. Observe odds for 2+ minutes | Odds should refresh every 10–15 seconds automatically | Odds remain static; require manual page refresh to update | High | P2 | In Progress | Dev investigating WebSocket connection
BG-004 | 28/05/2026 | Anthony Wambua | Bet Slip | Bet slip total miscalculates when more than 3 selections added | 1. Add 3 bets to slip 2. Add a 4th bet 3. Check total stake | Total stake = sum of all individual bet amounts | Total stake shows incorrect value (appears to drop one selection) | High | P2 | Open
BG-005 | 28/05/2026 | Anthony Wambua | Casino / Crash Game | Crash game multiplier freezes at 1.00x on iOS 17.4 | 1. Open Crash game 2. Place bet 3. Observe multiplier on iPhone (iOS 17.4) | Multiplier should animate upward from 1.00x until crash event | Multiplier stays at 1.00x; game appears to start but does not animate | High | P2 | Open | Only reproduced on iOS 17.4; iOS 16 unaffected
BG-006 | 28/05/2026 | Anthony Wambua | Withdrawal | Withdrawal history tab shows blank screen on first load | 1. Log in 2. Go to Account > Withdrawal History | List of past withdrawals displayed | Blank white screen shown; refreshing manually loads data correctly | Medium | P3 | Resolved | Fixed in build 3.2.2 — lazy load issue
BG-007 | 28/05/2026 | Anthony Wambua | Notifications | Push notifications for won bets not delivered on Android 14 | 1. Place a bet 2. Win the bet 3. Check notification tray (Android 14) | Push notification: 'Congratulations! Your bet on [match] has won.' | No push notification received; win only visible inside the app | Medium | P3 | Open
BG-008 | 28/05/2026 | Anthony Wambua | UI / Layout | Bottom navigation bar overlaps content on small screen devices | 1. Open app on a 5-inch screen device 2. Navigate to any main section | All content fully visible above the navigation bar | Bottom ~40px of content hidden behind navigation bar | Low | P4 | Open | Affects devices with screen height < 640dp
BUG SUMMARY |  |  |  | SEVERITY LEGEND
Total Bugs | 8 |  |  | Critical | App crash, data loss, payment failure — blocks release
Open | 6 |  |  | High | Major feature broken — workaround possible
In Progress | 1 |  |  | Medium | Feature partially broken — does not block release
Resolved | 1 |  |  | Low | Minor UI/UX issue — cosmetic or edge case
Critical | 2
High | 3
Medium | 2
Low | 1